C-CLARKE INTERNATIONAL INSTITUTE OF DIGITAL SCIENCES

Diploma in Advanced AI & Software Engineering  |  Batch 25/26

SMART HIRE

Work Breakdown Structure

WBS & Project Management Plan

| Program | Diploma in Advanced AI & Software Engineering |
| --- | --- |
| Batch | 25 / 26 |
| Assessment | Group Software Development Assignment |
| Deliverable | Project Management – WBS / Jira Board |
| Technology Stack | HTML / CSS / JavaScript, Python (FastAPI), PostgreSQL |
| Submission Date | 22 July 2026 |
| Prepared by | [Team Member Names – to be completed] |
| Document Version | 1.0 |

# Table of Contents

# 1. Introduction

## 1.1 Purpose

This document defines the Work Breakdown Structure (WBS) for the Smart Hire project and the supporting project-management artefacts required by the assignment, including the schedule, sprint plan, milestones, roles and responsibilities, a risk register, and the mapping of the WBS to the team's Jira board. The WBS decomposes the total scope of work into manageable work packages so that effort can be estimated, assigned, tracked, and verified across the team.

## 1.2 Project Overview

Smart Hire is a centralized digital marketplace that connects customers with skilled service providers across categories such as plumbing, electrical work, home maintenance, tutoring, cleaning, repairs, and technical support. Customers can discover, compare, and book trustworthy professionals, while providers can publish and promote their services. The platform also integrates at least one AI-powered feature to differentiate the customer experience.

## 1.3 Scope of This Document

The WBS covers the full software development life cycle of the project, from initiation through requirements, design, implementation, quality assurance, deployment, and viva preparation. Detailed database design is produced as a separate companion document and is referenced here as work package 3.2.

## 1.4 Technology Stack

| Layer | Technology | Notes |
| --- | --- | --- |
| Frontend | HTML, CSS, JavaScript | Responsive multi-page UI for customer, provider, and admin roles |
| Backend | Python – FastAPI | REST API, async request handling, OpenAPI/Swagger docs |
| Database | PostgreSQL | Relational store; pgvector & pg_trgm extensions for AI and search |
| ORM / Migrations | SQLAlchemy + Alembic | Data-access layer and versioned schema migrations |
| Authentication | JWT + bcrypt | Token-based auth with role-based access control |
| AI Layer | LangChain + LLM API / local LLM | Powers the AI feature (assistant, summarization, recommendation) |
| Version Control | Git + GitHub | Feature-branch workflow with pull-request reviews |
| Project Mgmt | Jira (or equivalent) | Epics, sprints, and task tracking aligned to this WBS |

# 2. WBS Approach & Conventions

Decomposition method. The WBS follows a hybrid phase- and deliverable-oriented decomposition. Level 1 is the project itself; Level 2 groups the work into the major phases of the software life cycle; Level 3 breaks each phase into concrete work packages that can be assigned to an individual and estimated in person-days.

The 100% rule. Each parent element fully represents the work of its children – the sum of the child packages equals 100% of the parent, with no work omitted and none counted twice.

Numbering. A hierarchical decimal code (for example 5.7) uniquely identifies every package and is reused as the reference key on the Jira board and in commit messages, giving end-to-end traceability from plan to code.

Work package definition. A Level-3 package is small enough to be completed by one owner within a single sprint and large enough to produce a verifiable deliverable, satisfying the 8/80 heuristic (between roughly 8 and 80 hours of effort).

# 3. Work Breakdown Structure

Smart Hire (Level 1) is decomposed into ten Level-2 phases and their Level-3 work packages, as shown below.

1.  Project Initiation & Management

1.1  Team formation & role assignment

1.2  Project charter & scope statement

1.3  Git repository & branching strategy setup

1.4  Jira board configuration (epics, sprints, workflow)

1.5  Sprint planning & backlog grooming

1.6  Risk management plan

1.7  Stand-ups, review meetings & recordings

1.8  Project closure & final report

2.  Requirements Engineering

2.1  Stakeholder identification

2.2  Requirements elicitation & analysis

2.3  Software Requirements Specification (SRS)

2.4  Use case modelling & diagrams

2.5  User stories & product backlog

2.6  Requirements review & sign-off

3.  System & Architecture Design

3.1  High-level (three-tier) architecture

3.2  Database design – ERD, schema, normalization (see DB Design document)

3.3  API contract design (REST / OpenAPI)

3.4  UI/UX wireframes & navigation flow

3.5  Authentication & authorization design (JWT, RBAC)

3.6  AI feature design & data-flow

3.7  Design review & baseline

4.  Database Implementation (PostgreSQL)

4.1  PostgreSQL environment & extension setup

4.2  DDL scripts (types, tables, constraints)

4.3  Indexes & performance objects

4.4  Seed / reference data scripts

4.5  Migration scripts (Alembic)

4.6  Database validation & testing

5.  Backend Development (Python / FastAPI)

5.1  Project scaffolding & configuration

5.2  ORM models & DB session layer (SQLAlchemy)

5.3  Authentication & authorization module

5.4  User & provider profile module

5.5  Service catalog & category module

5.6  Search & discovery module

5.7  Booking & scheduling module

5.8  Payment recording module

5.9  Reviews & ratings module

5.10  Notifications module

5.11  AI feature service integration

5.12  API documentation (Swagger / OpenAPI)

6.  Frontend Development (HTML / CSS / JS)

6.1  Project structure, base layout & styling system

6.2  Authentication & onboarding pages

6.3  Customer portal (search, detail, booking, history)

6.4  Provider portal (services, availability, bookings)

6.5  Reviews & ratings UI

6.6  AI assistant UI integration

6.7  Admin dashboard

6.8  Responsive & cross-browser polish

7.  AI Feature Development

7.1  Feature specification & model selection

7.2  Data preparation & prompt design

7.3  Backend AI endpoint & orchestration (LangChain)

7.4  Vector store / embeddings (pgvector)

7.5  Frontend integration

7.6  Evaluation, guardrails & cost controls

8.  Quality Assurance & Testing

8.1  Test plan & strategy

8.2  Test case design

8.3  Unit testing

8.4  Integration & API testing

8.5  System testing & UAT

8.6  Bug reporting & defect tracking

8.7  Regression & test-evidence compilation

9.  Deployment & DevOps

9.1  Environment configuration & secrets

9.2  Database deployment

9.3  Backend deployment

9.4  Frontend hosting / deployment

9.5  Smoke testing

9.6  Deployment guide

10.  Documentation & Viva Preparation

10.1  API documentation finalization

10.2  Testing documentation package

10.3  User & deployment guide

10.4  Presentation deck

10.5  Viva readiness (every member explains all components)

10.6  Repository & submission finalization

# 4. WBS Dictionary

The dictionary summarises each Level-2 work package: its key activities, primary deliverables, the primary owner role, and an effort estimate in person-days (PD). Owner roles: PL = Project Lead / Scrum Master, BE = Backend Engineer, FE = Frontend Engineer, DBE = Database Engineer, AIE = AI Engineer, QA = QA Engineer. In a small team, members hold more than one role.

| ID | Work Package | Key Activities | Primary Deliverable | Owner | PD |
| --- | --- | --- | --- | --- | --- |
| 1 | Project Initiation & Management | - Charter, scope, repo & Jira setup - Sprint planning, stand-ups, closure | Charter, Jira board, final report | PL | 6 |
| 2 | Requirements Engineering | - Elicit, analyse & document needs - Use cases, user stories | SRS, use case diagrams, backlog | PL / BE | 5 |
| 3 | System & Architecture Design | - Architecture, API & UI design - Auth & AI data-flow design | Design baseline, ERD, API contract | BE / DBE | 6 |
| 4 | Database Implementation | - Create types, tables, indexes - Seed data & migrations | DDL scripts, migrations, seed data | DBE | 5 |
| 5 | Backend Development | - Build all API modules & auth - Integrate AI service & docs | FastAPI service, OpenAPI docs | BE / AIE | 14 |
| 6 | Frontend Development | - Build customer/provider/admin UI - Responsive styling | Web client (HTML/CSS/JS) | FE | 12 |
| 7 | AI Feature Development | - Prompt design & orchestration - Embeddings & evaluation | Working AI feature + evidence | AIE | 6 |
| 8 | Quality Assurance & Testing | - Design & run test cases - Log & retest defects | Test cases, bug reports, evidence | QA | 8 |
| 9 | Deployment & DevOps | - Configure & deploy all tiers - Smoke test | Deployed app, deployment guide | BE / PL | 4 |
| 10 | Documentation & Viva Prep | - Finalise docs & slides - Rehearse viva coverage | Doc pack, deck, viva readiness | All | 5 |

Indicative total effort: ≈ 71 person-days across the team within the four-week window.

# 5. Project Schedule & Sprint Plan

The project runs as four one-week sprints between 24 June 2026 and the submission date of 22 July 2026, following an incremental Agile approach. Each sprint produces a demonstrable increment.

| Sprint | Dates (2026) | WBS Focus | Key Outcomes |
| --- | --- | --- | --- |
| Sprint 0/1 (Setup) | 24 Jun – 30 Jun | 1, 2, 3, 4.1–4.2, 5.1 | Charter & Jira live, SRS, architecture & ERD baseline, DB schema created, backend scaffolded |
| Sprint 2 (Core) | 01 Jul – 07 Jul | 4.3–4.6, 5.2–5.6, 6.1–6.3 | Auth, users, catalog & search APIs; DB seeded; base UI + auth + customer search/booking pages |
| Sprint 3 (Features) | 08 Jul – 14 Jul | 5.7–5.11, 6.4–6.6, 7 | Booking, payments, reviews, notifications; AI feature end-to-end; provider portal & assistant UI |
| Sprint 4 (Hardening) | 15 Jul – 21 Jul | 6.7–6.8, 8, 9, 10 | Admin dashboard, full QA cycle, deployment, documentation, presentation & viva rehearsal |
| Submission | 22 Jul | 1.8, 10.6 | Repository, documentation & demonstration submitted |

## 5.1 Milestones

| Milestone | Target | Exit Criteria |
| --- | --- | --- |
| M1 – Requirements & Design baseline | 30 Jun 2026 | SRS, use cases, architecture and ERD approved; schema created |
| M2 – Core platform demo | 07 Jul 2026 | Login, service catalog and search working over the API and UI |
| M3 – Feature-complete | 14 Jul 2026 | Booking, reviews, notifications and the AI feature all functional |
| M4 – Tested, deployed & documented | 21 Jul 2026 | QA evidence complete, app deployed, all documents finalised |
| M5 – Submission & viva-ready | 22 Jul 2026 | Repo submitted; every member can explain every component |

# 6. Roles & Responsibilities

Responsibility for each phase is summarised below using a RACI matrix (R = Responsible, A = Accountable, C = Consulted, I = Informed). Roles map to team members on the cover page.

| WBS Phase | PL | BE | FE | DBE | AIE | QA |
| --- | --- | --- | --- | --- | --- | --- |
| 1 Initiation & Mgmt | A/R | C | C | C | C | C |
| 2 Requirements | A | R | C | C | C | I |
| 3 Design | A | R | C | R | C | I |
| 4 Database | I | C | I | A/R | I | C |
| 5 Backend | I | A/R | C | C | R | C |
| 6 Frontend | I | C | A/R | I | C | C |
| 7 AI Feature | I | C | C | C | A/R | C |
| 8 QA & Testing | C | C | C | C | C | A/R |
| 9 Deployment | A | R | C | C | I | C |
| 10 Docs & Viva | A | R | R | R | R | R |

## 7. Risk Register

| Risk | L | I | Mitigation |
| --- | --- | --- | --- |
| Scope creep beyond core marketplace + one AI feature | M | H | Freeze scope after M1; new ideas go to a backlog, not the current sprint |
| Uneven member skills delay modules | M | M | Pair programming, shared coding standards, early spikes on risky areas |
| AI API cost, latency or rate limits | M | M | Cache results, set token limits, keep a local-LLM fallback path |
| Integration delays between frontend and API | M | H | Agree the OpenAPI contract in Sprint 0; use mock data until APIs land |
| Compressed four-week timeline | H | H | Prioritise must-have user stories (MoSCoW); keep Sprint 4 as a buffer |
| Member cannot explain a component at viva | M | H | Rotate reviewers; every package reviewed by a second member before Done |

L = Likelihood, I = Impact (L / M / H).

# 8. Jira Board Mapping

The WBS maps directly onto the Jira board so that planning and execution stay traceable:

- Epics – one per Level-2 phase (10 epics, keyed by WBS ID).

- Stories / Tasks – one per Level-3 work package, linked to its parent epic and a sprint.

- Sub-tasks – fine-grained steps within a story, assigned to an individual owner.

- Workflow columns – Backlog → To Do → In Progress → In Review → Done.

- Estimation – story points per item; sprint capacity tracked on the burndown chart.

Each commit and pull request references the WBS / issue key (for example “SH-5.7: implement booking creation endpoint”), giving end-to-end traceability from this plan through Jira to the Git history.